Sunday 7th July 2024, 10.30am Regatta start All Adult members to be at the Clubhouse by 0615hrs please, Juniors ASAP

| Nr. | Jobs to be done | Who | Comments | When By | Complete? |
| --- | --- | --- | --- | --- | --- |
|  | Confirm date with DHB and add to DHB Portal | Jacky |  | Oct 2023 | Complete |
|  | Advise swimmers | Jacky |  | Oct 2023 | Complete |
|  | Advise Wetwheels | Jacky |  |  | Complete |
|  | Advise Lifeguards | Jacky |  |  | Complete |
|  | Book Safety Launch’s x 2 for the day - Stuart/James W’sports - Chris Danican | Jacky | Awaiting confirmation from Stuart Need to confirm details with Chris |  | Pending |
|  | Confirm Helpers for Safety Boats x 2 (1 per boat) |  |  |  |  |
|  | Confirm Umpires Boat (Mariner III unavailable) Chris Danican | Jacky | Need to confirm information with Chris |  | Pending |
|  | Need 3 chairs for the Umpires boat – to be taken to the new ramp? | Jacky | Not required this year |  | N/A |
|  | Invite Club | Jacky |  |  | Complete |
|  | Write to Previous sponsors re sponsorship | Jacky |  |  |  |
|  | New Sponsors | All |  |  |  |
|  | Sponsorship notice on FB | Jacky |  |  | Complete |
|  | Order Prizes | Jacky |  |  | Complete |
|  | Order 2nd Place Medals for Junior races | Jacky | Collection 24Jul2024 |  | Complete |
|  | Regatta Race Draw | Jacky/Tony |  |  |  |
|  | Type of Programme | Jacky |  |  |  |
|  | Book and Send to printers | Jacky |  |  |  |
|  | Distribute programme to sponsrs | Jacky |  |  |  |
|  | Electricity – From DHB FOR PA Only | Jacky |  |  |  |
|  | Extension Leads for PA |  |  |  |  |
|  | Ask for use of Kiosk – For Water Boilers | Jacky | Electricity supply needs to be separate from PA |  |  |
|  | Confirm First Aiders | Jacky | Checking with DHB Seb? |  |  |
|  | Radio for First Aider | Jacky |  |  | Complete |
|  | Order Radio’s:– ensure all on same channel | Jacky | 1 x Umpires Boat and 1 for Starters, 2 for Safety Boats, 1 for First Aider | Collection Friday 5th July 2024 |  |
|  | Float for Regatta from Bank | Jacky |  | 9th June 2023 |  |
|  | Cash Boxes | Jacky |  |  |  |
|  | Collect Prizes/Tankards | Jacky & Maria |  | Fri 5th July |  |
|  | Sort and Number for Prize Giving | Jacky |  |  |  |
|  | Clean Trophies | Jacky |  |  |  |
|  | Buy Burgers, Water, Tesco etc | Jacky & Maria |  | Fri 5th July |  |
|  | Tombola - box available at the club ? |  | Not sure we will have enough help to do this this year |  | N/A |
|  | Food – Members to bring down food to sell at the regatta eg, Sandwiches, Pasta, Cakes, Crisps, Fruit etc | All |  | Day of regatta |  |
|  | Food/Drink: set up tables for food/drink/BBQ area |  |  | 08.30 am |  |
|  | Food/Drink Prices and hanging burger notices etc |  |  | 09.00 am |  |
|  | Put up bin bags around food area |  |  | 06.30am |  |
|  | Hang up signage advertising food etc |  |  | 09.00 am |  |
|  | Commentator | Jacky | Curly ? | All Day |  |
|  | Pump up Buoys and check ropes and weights - We Need 14 minimum and 2 x 5m Bouys |  |  | By Tuesday prior to regatta in case we have to purchase more |  |
|  | Set up turns and 5m bouys |  |  | Fri/Sat |  |
|  | Tea Urns Check working |  |  |  |  |
|  | Clean prior to the day |  |  |  |  |
|  | Check we can use the BBQs | Nick |  |  |  |
|  | Man regatta phone hot line | Maria |  | 06.15 am |  |
|  | Make decision about whether regatta on or off – then | Maria/Cam/ Jo? |  | 06.00 am |  |
|  | Notify Jacky (07557 193798) so she can notify Umpires and sponsors etc if cancelled | Maria to call/text Jacky |  | 06.05 am |  |
|  | Notify all members of ON/OFF | Maria |  | 06.10am |  |
|  | All relevant boats onto Beach | All Members |  |  |  |
|  | Gazebo’s 1 x First Aid 2 x Food 1 x Start line – Needs to be weighted down really well with pebbles as well as water holders if windy (water holders blow away easily). |  | Food and first aid tents worked well outside the Kiosk in 2023. | 07.30 am |  |
|  | Check First Aid Kit is up to date | Maria? |  |  |  |
|  | Set up Start/Finish line |  |  |  |  |
|  | PA Set Up | The Ratzkins |  | 08.00 am |  |
|  | Dig in Wires |  |  | 08.30 am |  |
|  | Rope of starting area Oil Drums for Start line & Poles |  |  | 08.00 am |  |
|  | Set up starting rostrum: Chairs/tables |  |  | 08.00 am |  |
|  | Take up starters flags, Radios and finish horn etc | Jacky |  | 08.00 am |  |
|  | Food for Umpires Launch Collect food/drink/water for umpires/safety launches and put in cool bag (+ cubes) | Jacky | Umpire Boat x 3 Safety Boats (2) x 2 | 09.00 am Take to start tent |  |
|  | Check clubhouse is clean and tidy/safe in accordance with our risk assessment and hazards on the day | Cameron |  | By 09.00 am |  |
|  | BBQ – Set up/Light | Nick/Neil ? |  | 08.00 am |  |
|  | Coals | Nick ? |  |  |  |
|  | Man BBQ for the Day | Nick / Neil ? |  | 09.00 am |  |
|  | Food Prices |  |  |  |  |
|  | Food/Drink: a) set up tables for food/drink/BBQ area in briefing room of clubhouse |  |  | 08.30 am |  |
|  | Food/Drink Prices and hanging burger notices etc |  |  | 09.00 am |  |
|  | Put up bin bags at food tents etc |  |  | 06.30am |  |
|  | Hang up signage advertising food etc |  |  | 09.00 am |  |
|  | Distribute Float for regatta for food/drink | Maria |  | 09.00 am |  |
|  | Sales Floats and Cash | Maria |  | All day |  |
|  | Marshall trailers onto Promenade and ENSURE THEY PARK TRAILERS AS PER INSTRUCTIONS All boats to be remove so no restrictions to residents etc | Brendon? |  | 08.00 am onwards |  |
|  | Regatta Secretary | Jacky |  | All Day |  |
|  | Dover Scratchings/Late Entries to Jacky/Julie by 09.00 am | Jacky/Julie via Maria |  | 09.00 am |  |
|  | Assistant on Day | Julie |  | All Day |  |
|  | Captains/Cox’n/Safety Mtg | Cam/ Maria |  | 10.00 am |  |
|  | Spare kit for loan – ENSURE ITS GIVEN BACK AFTER YOUR RACING IS OVER ! | Maria |  | On Day |  |
|  | Programme selling ?? | At food tables |  | All day |  |
|  | Burger run/additional items – runner required | Maria? |  |  |  |
|  | Clean Trophies |  |  |  |  |
|  | Set up set up tables and cloths and trophies etc before start of last race. | Jen and Chrissy |  |  |  |
|  | Paperwork for Prize Giving | Jacky |  |  |  |
|  | Post Regatta – a) tidy up beach b) put equipment away in clubhouse in tidy fashion c) collect buoys d) take down start poles e) take down PA system e) clean BBQs | ALL All Ratzkins |  |  |  |

PLEASE DON’T GO HOME or TO THE PUB WITHOUT HELPING TO CLEAN UP AFTER THE  REGATTA.  THANK YOU 